## Progress Tracking
Task | Status
Kağan Erdem
Gather project requirements | Completed
Analyze user needs based on business types | Completed
Create main user flow diagram | Completed
Create basic website sitemap | In Progress
Plan user login design for the admin panel | In Progress
Define reservation form requirements | Not Started
Design the database schema | In Progress
Prepare homepage prototype | Not Started
Create a GitHub repository | Completed
Open project management "issues" on GitHub | Completed
Assign tasks through GitHub issues | Completed
Integrate developed modules and perform initial testing | Not Started
Ahmet Hilmi Büber
List service categories for different business types | Completed
Define business registration form requirements | Completed
Design business profile page | In Progress
Design reservation calendar interface | In Progress
Design reservation history page for users | Completed
Plan email notification system | Completed
Develop backend for reservation time management | Completed
Code the reservation management screen for the admin panel | In Progress
Implement the email notification system | Completed
Develop the business profile update function | Not Started
Develop reservation cancellation/update system for admin panel | Not Started
Conduct testing for developed modules | Not Started
Buğra Sarıkaya
Research server and domain options | Completed
Prepare deployment plan | Completed
Create testing scenarios | In Progress
Support frontend development of the website | Completed
Develop reservation conflict check system | Completed
Implement server-side error handling | In Progress
Develop user reservation creation module | Completed
Develop user registration/login module | Completed
Implement reservation cancellation module | Not Started
Prepare project progress report | In Progress
Conduct load testing (simulate multiple users) | Not Started
Prepare and finalize project demo for presentation | Not Started